## Team working Areas
Task | Description | Owner | Start Date | End Date | Percentage
UI Dashboard | Enhancing UI dashboard by incorporating - Knitwell Logo - Homepage - Extra parameters - scheduler - Report integration, environment and tags | Somasundaram | 19.05.2026 | 09.05.2026 | 60
Skillux vs Alternatives | Image recognition and interaction using Typescript libraries. - Tesseract is used for text extraction - OpenCV for image processing - nut.js for keyboard and automation actions. - desktop-screenshot | Ganesh
Mobile Testing using Appium | Appium library integration with AFTA - Playwright - Android - Basic interactions reusables - Driver set-up - Lambda configuration - Reporting | Dinesh Damodharan
Performance tool evaluation | Evaluate Neoload, CloudTest and jmeter(APTF Framework) - What can't be achieved using APTF comparing to NeoLoad and CloudTest - Features in all three tools - Reporting etc., | Muthu
Framework readme | Framework readme document update | Dhanush
Legacy framework exploration |  | Sathesh
AFTA documentation | AFTA documentation as an input to AI agent | Midhu
Test spell |  | Midhu
Self-Healing Enhancement | Enhancing self-healing for AFTA-Playwright - Use AI as a fallback - Generate page specific smart locators as the alternate locators | Nivetha
Auto-POM Enhancement | Enhance Auto-POM chrome extension - To generate smart locators first - Enhance x-path strategy and page.getByRole logic | Dhanush
Automation KT | KT Plan Day 01 : - E-Commerce platform - Framework structure and execution flow - Premium brands e-com - Automation suites and Jenkins execution Day 02 : -Followed by POS and MAO, CHICOS & other brands Day 03 : - Sprint activities and sign-off process Day 04 : - Maintenance activities and Jenkins Day 05 : - Reporting & Validation Day 06 : - Defect tracking & Test Management Day -07 : - Branching strategy for different brands Day -08 : - Effort estimation and sprint planning /Product Backlog/ Sprint Backlog/Re-testing | Vinoth & Team
Existing Application Performance Framework/Script Analysis | Debug and Analyse existing framework components. Execute scripts in local and LambdaTest | Vinoth & Team
Maintenance Support | Involve team in ongoing maintenance support once KT is completed | Vinoth & Team
| Framework exploration | Dinesh Ramakrishnan, Vivedhini

## Daily Status - Sangamithra
Status Update
Date | Completed | Inprogress/Yet to start | Blocker | Comments | Start Date | Expected End Date
2026-05-22 |  | Exploring and adding Parameters in Afta runner page
2026-05-25 | Added Parameters in Afta runner page successfully | Exploring on adding scheduler to the runner page
2026-05-26 |  | Exploring on adding scheduler and environment to the runner page. Also working in Report generation in Jenkins
2026-05-27 |  | Added environment and got review from Soma. working on enhancing the added environment feature. Exploring on adding Scheduler to the Afta Dashboard
2026-05-29 | Worked on the Dashboard page and fetched reports from Jenkins successfully | Working on implementing the scheduling functionality in the dashboard. |  |  | 19.05.2026 | 09.06.2026
2026-06-01 | Added scheduler to the Afta Dashboard successfully | Working on enhancing the home page freatures in Afta Dashboard |  |  | 01.06.2026 | 03.06.2026
2026-06-02 | Worked in html and .scss file to Add info icon, brief definition of the tabs and loading of the test results in home page and completed successfully. | Working on enhancing the theme of the home page freatures in Afta Dashboard. Also preparing PPT for Demo |  |  | 01.06.2027 | 03.06.2027
2026-06-03 | fetching reports from Jenkins, Added params, homepage and logos | Worked on the new Reports page UI enhancement. |  |  | 01.06.2027 | 03.06.2027

## Daily Status - Vivedhini
Status Update
Date | Completed | Inprogress/Yet to start | Start date | end date
May 21st | premium brand framework set up completed | Framework exploration
May 22nd | Premium brand exploration
May 25th | Premium brand exploration | cucumber BDD KT
26/05/2026 | Executed the premium brand Sanity TC. Added my lambda credentials in framework | Executing the premiumbrand Sanity TC's. using recent updated code | NA | NA
27/05/2026 | Executed and filed the Premium brand framework , setup the allure report and setup the local extent report | Analyzing the RCA for failed test cases | NA | NA
2026-01-06 | Executed sanity suite TC for LoFT and Ann Taylor and shared the failure report of LOFT with vinoth | RCA for failled TCs of Ann Taylor sanity suite is in progress | 2026-06-01 | 2026-06-02
2026-06-07 | Analysing failure of LOFT sanity suite and fixing it | 3/6 TC of loft is fized. yet fix the rest | 2026-06-02 | 2026-06-03
2026-06-08 | Analysing failure of LOFT sanity suite and fixing it | 4/6 fized | 2026-06-02 | 2026-06-04
Sanity Execution Report - May 27 2027
| Total Test cases | Passed | Failed | Time Taken
Loft | 80 | 66 | 14 | 11 mins 56 sec
Ann Taylor | 81 | 63 | 18 | 14 min 19 sec

## Daily Status - Somasundaram Mut
Status Update |  | Due Date: 9/6/2026 -- Current progress: 70%
Date | Completed | Inprogress/Yet to start | Blocker | Comments | Start Date | Expected End Date
May 26th | fetching reports from Jenkins, Added params, homepage and logos | Scheduler | While fetching jenkins reporter, facing bloker issue in Jenkins then connected with NSA team and now resolved |  | 19.05.2026 | 09.06.2026
May 27th | fetching reports from Jenkins, Added params, homepage and logos | Scheduler | Exploring on adding scheduler and environment to the runner page. Also working in Report generation in Jenkins
May 29th | fetching reports from Jenkins, Added params, homepage and logos | Scheduler | Added environment and got review from Soma. working on enhancing the added environment feature. Exploring on adding Scheduler to the Afta Dashboard
2026-06-01 | fetching reports from Jenkins, Added params, homepage and logos | Scheduler | Working on implementing the scheduling functionality in the dashboard.
2026-06-02 | fetching reports from Jenkins, Added params, homepage and logos | Scheduler | Working on enhancing the home page freatures in Afta Dashboard
2026-06-03 | fetching reports from Jenkins, Added params, homepage and logos | Reports | Worked on the new Reports page UI enhancement.
2026-06-04 | fetching reports from Jenkins, Added params, homepage and logos | Reports | Worked on the additional page UI enhancement- Added new inputs on Reports Page

## Daily Status - Dinesh D
Status Update
Date | Completed | Inprogress/Yet to start | Blocker | Comments
2026-05-21 | * Appium Mobile App testing reusable interaction methods | * Appium Mobile App testing report
2026-05-22 | *Reporting - Report Portal, Playwright report & Allure Report | * Failure screenshot is not attached in report - checking on that * Validating the reusable methods
2026-05-25 | *Codespell setup with Bitbucket configuration | * Exploring the Codespell AI tool to generate the automation script with Our AFTA Playwright Typescript * Generate the automation script AutPom Input
2026-05-26 | * Explored Codespell AI tool to generate the automation script with Our AFTA Playwright Typescript * Generated the automation script with doc AutPom Input | * Generate the automation script with AutPom Input from Repo * Planning to Explore the Playwright MCP with Claude
2026-05-27 | * Explored Codespell AI tool to generate the automation script with Our AFTA Playwright Typescript and Playwright MCP with Claude | * Planning to incorporate the review comments form Vinoth -Appium mobile automation
2026-05-29 | Appium Mobile Automation - incorporating the review comments Environment-Driven Mobile Driver Factory Approach Mobile common steps implementation | *Analysing the Data layer validation and derive the TC * Exploring the Loctaor declaration for ios & andorid devices
2026-06-02 | creating the sample script for datalayer validation and analysing the new approach to reusable E2E Test scripts | Analysing the new approach to create reusable E2E Test scripts
2026-06-03 | worked on the base Framework foundation and reporting structure for data layer validation | Framework foundation and Base Test script . Validation coverage expansion for remaining pages is in progress
2026-06-04 | Worked on the base Framework foundation and updated the reporting structure & summary for data layer validation And also analysing the All page Variables. | ⁠Analysis of all DataLayer variables and implementation of reusable methods for expected value handling.

## Daily Status - Midhu
Status Update
Date | Completed | Inprogress/Yet to start | Blocker | Comments | Start Date | Expected End Date | Status
2026-05-21 | Attended KT sessions. Prepared the documentation for the AFTA Playwright with TypeScript framework and shared it for review.
2026-05-22 | Update the AFTA document - AFTA documentation as an input to AI agent ReadMe doc + More details --> Document Attended KT on Test Spell Created detailed documentation on KT - Day 3
2026-05-25 | Created detailed documentation on KT - Day 4 | Update the AFTA document - AFTA documentation as an input to AI agent based on review comments from Dhanush
2026-05-26 | Updated AFTA document based on the review comment and shared to Dhanush for review Created detailed documentation on KT - Day 5 Explored on Softspell KT
2026-05-27 | Created detailed documentation on KT - Day 6 Executed PI-P2 testcases in Premium brand | Need to Execute pending P1P2 premium brand testcases
2026-05-28 | Analysed and executed Premium SFCC test cases. Identified challenges and shared detailed observations to Vinoth |  |  |  | 2026-05-28 | 2026-05-28 | Completed
2026-06-01 | Worked on creating Sprint level details on confluence page | Need to Update the AFTA document based on review comments |  |  | 2026-06-01 | 2026-06-02 | InProgress
2026-06-02 | Analyzed Cart and All Pages component test cases to understand functionality, identified merge/remap opportunities, and documented the test cases with missing or unclear expected results. | Need to perform test case analysis on rest of the test components in Premium - Master regression sheet |  |  | 2026-06-02 | 2026-06-04 | InProgress
2026-06-03 | Performed manual analysis of Ann Taylor & LOFT ExecutionEngine test cases, identifying missing expected results and test case merge/remap opportunities. Documented findings and drafted the mail for review and sharing. | Need to perform test case analysis on rest of the test components in Premium - Master regression sheet |  |  | 2026-06-03 | 2026-06-04 | InProgress
2026-06-04 | Worked on Updating the AFTA document based on review comments |  |  |  | 2026-06-04 | 2026-06-04 | InProgress

## Daily Status - Ganesh
Status Update | Due Date: 9/6/2026 -- Current progress: 80%
Date | Completed | Inprogress/Yet to start | Blocker | Comments
2026-05-21 | Nil | * Parameterisation of default global values is done. * Optimizing waits. * Enhancing Parameter suggestion & function description.
2026-05-22 | * Parameterisation of default global values is done. | * Optimizing waits. * Enhancing Parameter suggestion & function description.
2026-05-25 | * Parameterisation of default global values. * Optimizing waits. * Enhancing Parameter suggestion & function description. | * Optimizing ocr functions to filter out junk values.
2026-05-26 | * published the npm package. * optimizing image processing by actively using sharp library. * demo given to the team and got feedback. | * Optimizing ocr functions to filter out junk values. * Need to explore the suggestions given by the team.
2026-05-27 | * Optimizing OCR functions. | * Working on index based searching for OCR.
2026-05-29 | * Optimizing ocr functions to filter out junk values. * Working & testing the tool accross various resolutions. * index based searching for OCR based functions. | * creating the final test case to test on other systems. * remaining enhancements to OCR based on the existing orPOS OCR settings (ex: whitelisting, dpi etc)
2026-06-01 | * creating the final test case to test on other systems. * remaining enhancements to OCR based on the existing orPOS OCR settings (ex: whitelisting, dpi etc) | * Working on optimizing the resolution aspect for image matching to reduce the execution time further. * Functional Syntax & settings enhancement. * Clean up functions such as cache & OCR terminations should be written.
2026-06-02 | * optimized the resolution aspect for image matching to reduce the execution time further. * Functional Syntax & settings enhancement is completed. | * Clean up functions such as cache & OCR terminations should be written. * Exploring the possibility & fesability of using AI tools at any given step.
2026-06-03 | * Clean up functions such as cache & OCR terminations should be written. | * Exploring the possibility & fesability of using AI tools at any given step. * Identified the need to adding more helper funtions (popups, alerts, cmd input etc).
2026-06-04 | * Optimized image matching performance in Visor by improving template matching logic and reducing image search execution time significantly. * Added automatic display scaling detection and enhanced configuration handling to improve compatibility across different screen resolutions and DPI settings. * Implemented command execution utilities ("exec" and "execDetached") to enable running system commands directly from Visor automation scripts. * Added clipboard-based text paste functionality, reducing text entry time and improving overall automation execution speed. * Performed end-to-end Outlook PWA automation testing and validated performance improvements, reducing total workflow execution time considerably. | * Implementation of popup, confirmation, and input dialog helper functions. * Investigation of alternative OCR engines and advanced text recognition improvements. * Additional framework utility functions for notifications and interactive user prompts.

## Visor - Ganesh
Description- Area need to Fixed | Status | Comments
NPM package development | Completed | Nil
Parameterisation of default global values | Completed | Nil
Optimizing waits. | Completed | Nil
Enhancing Parameter suggestion & function description. | Completed | Nil
package publishing to NPM | Completed | Nil
Optimizing ocr functions to filter out junk values. | Completed | Nil
index based searching for OCR. | Completed | Nil
enhancements to OCR based on the existing orPOS OCR settings (ex: whitelisting, dpi etc) | Completed | Nil
optimizing the resolution aspect for image matching to reduce the execution time further. | Completed | Nil
* Clean up functions such as cache & OCR terminations should be written. * Exploring the possibility & fesability of using AI tools at any given step. | Completed | Nil
* Implementation of popup, confirmation, and input dialog helper functions. * Investigation of alternative OCR engines and advanced text recognition improvements. * Additional framework utility functions for notifications and interactive user prompts. | In Progress | Nil

## Daily Status - Dhanush
Status Update
Date | Completed | Inprogress/Yet to start | Blocker | Comments
20/05/2026 | Implemented Selenium locator generation and Page Class generation. Enhanced locator naming logic to generate meaningful and readable locator names by leveraging associated label text from the UI. | Radio button locator generation is currently not working as expected and requires further implementation and validation.
21/05/2026 | * WebDriverIO --> Rename to Selenium - Done, Meaningful names generation for locator - Completed | Method name generation enhancement is pending and will be taken up next.
22/05/2026 | ReadME Document: completed the review of Readme and added to the framework AFTA documnet : Review has been completed shared the reviwe comments to Midhu | Auto Pom: The improvements for locator generation and page function name generation have been completed. Currently, the button & link name generation logic is facing some issues, and I am actively working on resolving them.Apart from this, locator and function names for checkboxes, dropdowns, input fields are now being generated with more meaningful and reliable names using the label fallback technique. The radio button locator generation issue is still pending validation and refinement. I plan to complete this by tomorrow EOD and target the overall delivery by Wednesday.
25/05/2026 | Radio button element generation was completed | element name generation for button and link enhancement is in progress
26/05/2026 | Element and function name generation was completed, and ID, xpath dynamic value generation issue fixed | Plan to give the KT to the team and based on the Vinoth review comments yet to work on it
27/05/2026 | Selfhealing - xpath, css, role locator generation enhancement was completed and fixed count issue fallback and element name run time generation was completed | Need to fix the special character handling, indexing issues, and removal of other unreliable attributes from the Auto POM locator generation process.
29/05/2026 | Worked on data layer validation exploration and test case sheet generation
2026-01-06 | llm index returning issue resolved | Enhance the dynamic id generation and for some elements the locator is not generated
2026-02-06 | Enhanced the fallback logic and updated the locator prompt , added the delete button to remove all the generated element completed percentage- 95% | Page function name generation issue, final version enhancement
2026-03-06 | Worked on auto pom page function name generation fixing and created the qrchitecture diagram
2026-04-06 | Prepared the AFTA rest assured framework to show the demo to fagun and enhanced the delete button addition and few enhancement got added

## Daily status - Sathesh
Status Update
Date | Completed | Inprogress/Yet to start | Due date | Blocker | Comments
20/05/2026 | Completed the Documentation for Knitwell KT | Exploring the premium brands framework |  | NA | NA
21/05/2026 | Exploring the Legacy brand Framework and raised request for java, python, nodejs, jenkins and source tree. | Exploring the legacy brand framework |  | NA | NA
22/05/2026 | Give KT for Legacy brand framework and Explore the same framework | Exporing the Legacy framework |  | NA | NA
25/05/2026 | Explored in Integration of Claude desktop and MCP. | Exporing the Legacy framework and planning to migrate to Playwright |  | NA | NA
26/05/2026 | Explored the Integration of MCP in cluade desktop. Executed the Legacy brand Sanity TC. Added my lambda credentials in framework | Executing the Legacy brand Sanity TC's. using recent updated code |  | NA | NA
27/05/2026 | Executed and filed the Legacy brand framework 4 Trials, setup the allure report and setup the local extent report | Analyzing the failure in desktop LB and Executed the LB Iphone |  | NA | NA
29/05/2026 | Worked on Legacy framework setup and created branch | Need to analyze the failure for LB Desk and fix it |  | slowness of VDI and often update of Eclipse | NA
2026-01-06 | Clone a new LB framework.Analyzed and Fixing the legacy framework testcases | Fixing the legacy framework testcases | 2026-02-06 | slowness of VDI and often update of Eclipse | NA
2026-02-06 | Completed the failure analysis of today's execution. | Triggered the Execution of LB ios mobile |  | slowness of VDI and often update of Eclipse

## Daily status - Nivetha
Status Update |  |  | Due date
Date | Completed | Inprogress/Yet to start |  | Blocker | Comments
20/05/2026 | Self healing Architecture KT | Analysis of the framework |  | NA | NA
21/05/2026 | Understanding db connectivity, healing engine | Started with the smart locators |  | NA | NA
22/05/2026 | Completed the study of smart locators | Analysis of the browser actions and implementation of each action functions |  | NA | NA
25/05/2026 | Worked on creating complex html version files and running them separately as part of the local host and trying to test if the healing works properly. | Milestone 1: Testing if the smart locators works fine along with the order of priority |  | NA | NA
26/05/2026 | Created dedicated validation scenarios to prove that: Healing strictly follows the configured priority order. Lower-priority strategies execute only after higher-priority failures. Locator fallback behavior works consistently across DOM changes between V1 and V2 pages. CSS/XPath are used only as final fallback mechanisms. Enhanced the debugging and observability layer by: Printing locator strategy names and actual locator expressions in console logs. | To check various combinations of xpaths , check if the dom contexts are properly minimised and sent to AI, check the token values for AI hit. |  | NA | Milestone : Major priority - xpaths and dom minimisation check after confirming the smart locators logic
27/05/2026 | Xpath combinations - end to end check, and dom minimisation in progress | To check various combinations of xpaths , check if the dom contexts are properly minimised and sent to AI, check the token values for AI hit. |  | NA | NA
29/05/2026 | Worked on checking the new xpath and css enhancement , running script to check the count uniqueness of the healed locator , Also worked on running the parallel automation and recorded the challenges in the sheet | Currently working on the locator values correctness in the DB tables | Testing can be done before June3 - tentative | NA | NA
2026-01-06 | Worked on xpath combinations,css locators | Working on the removal of indexed xpaths from generated locators and also validating the special characters behaviour in locators | June 3 - tentative | NA | NA
2026-02-06 | Completed adding the rejection logic for indexed locators , added output formatting to validate the locators combination values, analysed the framework with respect to dynamic ID's and regex logics | More scenarios to be run for checking dynamic ID's, regex workings, single element multiple locators - trying to validate all possible scenarios with talbots website | June 3 - tentative | NA | NA
2026-03-06 | Completed testing all the dynamic ID's regex workings and basic home page smart locators generation script for talbots webpage. Also worked on adding checks for hidden elements while generating locators - added inEnabled() function along with waits and isVisible() functions wherever necessary. | Testing for screenshots in AI fallback - considered as noise or proper inputs, comparing confidence scores with and without screenshots scripting started, once this is completed , will start testing for iframe websites against our framework | June 4 to 5
2026-04-06 | Completed testing the AI Fallback mechanism, added stronger prompts and modified few regex values that AI can understand. | End to end scripting in talbots is in progress and also should review and discuss about screenshots and iframe logics | 2026-06-05

## Auto Pom -Dhanush
Description- Area need to Fixed | Status | Comments
Locator Name generation enhancement | Completed
Function name generation enhancement | Completed
Radio button element generation | Completed
Selenium locator and function generation implementation | Completed
WebdriverIo removal from code | Completed
Xpath and ID containes dynamic value like "#_0lMVaorEHZiXwcsPoZ6RiA4_37" | Completed
Uniqness has to check for label, text,alttext, title, placeholder | Completed
page function name generation issue | Completed
Over all locator removing button add on | Completed

## Self-Healing-Nivetha
Sno | Recommendation | Description | Why need this | Review
1 | Encryption of data | The screenshots and dom can expose potential sensitive data and hence can display client credentials or customer data | This can be done especially for production runs | We are using Azure OpenAI hosted within our organization's Azure environment, where the data is processed within Azure and is not used to train public OpenAI models. However, any DOM content, screenshots, or application data sent to the service is still transmitted outside the application boundary for processing. To mitigate this, we are minimizing the amount of data being sent by sharing only the relevant element context, locator details, and metadata required for self-healing, rather than transmitting the entire DOM or full-page screenshots.
2 | Similarity Matching | Currently, we are getting the old dom and new dom details and storing them but not comparing them | If we compute a similarity score, we can simply avoid AI hitting -> cost reduction | DOM similarity can help reduce AI calls, but it may not always be reliable. Modern applications frequently generate dynamic IDs, classes, and structural changes that can significantly alter the DOM without affecting the target element. Conversely, the DOM may remain largely similar while the actual locator becomes invalid. Therefore, relying solely on DOM comparison could lead to inaccurate decisions
3 | Retry Policy | Retrying the failed locators before starting the self healing engine | Most of the failures might be of various issues like slow API, hence retry logic will fix most of the failures before AI step | This is already in use
4 | Removal of hard coded API keys | Exposing our security keys currently | Security Issue | This will done once after enhancement completed
5 | Locator Uniqueness Validation | There should be only one visible element before accepting the healing | Currently, we dont have a count check of the new locator found, If we have a strong count validation, it can avoid multiple matches
6 | Report or dashboard creation | To track the workings, we can create a report for improving | 1. Healing rate 2. Flaky tests 3. AI usage 4. average confidence score | We will have the required reporting logs available, including details of the failed locator, healed locator, and the corresponding healing actions. Regarding dashboard creation, we need to discuss and evaluate the approach with Vinoth, as we already have the QA Dashboard Portal developed by Soma.
7 | Multi AI Fallback | Currently, we are relying on one AI model | In future we can use multiple AI systems to guarantee the 100 percent AI healing | We are not solely relying on AI for self-healing. The healing process first checks the locator information stored in the database and attempts recovery using the existing data. Only if a suitable match is not found through the database lookup do we invoke AI as a fallback mechanism. This approach helps reduce AI dependency, improves performance, and minimizes overall AI usage and cost.
8 | Iframe Support | Without iframe support: extractElementMeta() fails buildLocator() fails isValidLocator() fails AI healing may generate valid locator text but in wrong DOM context Screenshots may capture wrong area Healing fails even though element exists | Currently, we are not supporting iframes- but in modern web applications, we might miss out on this | In our current setup, this approach should work. However, we need to ensure that the solution is generic enough to support different types of applications and UI frameworks. Since each application may have different DOM structures, naming conventions, and locator strategies, we should validate the implementation across multiple applications and ensure that the logic is not tightly coupled to a specific framework or application structure.
9 | Screenshots format(Base64) | Your framework currently assumes: OLD SCREENSHOT + NEW SCREENSHOT ↓ AI understands visual difference ↓ AI predicts locator But in reality (with standard text LLM flow): OLD SCREENSHOT + NEW SCREENSHOT ↓ Huge unreadable Base64 strings ↓ Consumes tokens ↓ Little to no healing value So currently, the healing success is actually coming mostly from: smart locators outerHTML DOM comparison accessibility attributes context DOM locator metadata —not from screenshots. | We have to check if our model is sufficient enough to understand the images /not | Need to check with Vinoth
10 | Few browser actions can be added | double click right click drag and drop Multi tab support missing File validation after uploading | Currently , we dont have these actions in the browser actions repo, complex sites may require these actions
11 | Element_name uniqueness | In the db repo file, currently we have mentioned it as element_name assuming that it is globally unique- | So, if we have parallel pages containing the same element_name, then system gets confused, my suggestions- we can page the primary locator/exact url along with the element whenever necessary
12 | on conflict(element_name) | Might be risky for parallel processing | To test
13 | regex pattern check | More regex expressions can be added | To test
14 | Checking for hidden elements along with assertion | Currently , we have waits, count check and visible assertion but we can also add inEnabled() to ensure proper finding of all locators | To be added
15 | Rejection of indexed xpaths | Addition of rejection logic for indexed xpaths | Done
16 | Fallback engine | Mismatch of column names - context dom and full dom | To review the select query

## Daily Status - Dinesh Ram
Status Update
Date | Completed | Inprogress/ Yet to Start | Blocker | Comments
20/05/2026 | * Went through Javascript Typescript documentation from Dhanushkodi | To go through remaining Javascript Typescript documentation from Dhanushkodi | NA | NA
21/05/2026 | * Went through Javascript Typescript documentation from Dhanushkodi * Java Installation and dependency fixage in POM.XML * Eclipse Setup in Local machine with help of Helpdesk | To analyse the Page object class in Cucumber Framework | NA | NA
22/05/2026 | * Day 1 analysis of Cucumber Framework and understood rough idea on Test run from feature file > Step definitions > Page Classes > Element Locators (yml) * Driven call about test run flow understanding | Planned to explore the framework more and work on review comments | NA | NA
25/05/2026 | * Analysed Login script functionality * Prepared Day 4 KT documentation | Planned to work on designing Common action class for Login multiple brands | NA | NA
26/05/2026 | * Prepared FW approach for easy access of Common & Brand Specific Locators | Planned to enhance the FW approach for easy access of Common & Brand Specific Locators, with feedback comments from Vinoth | NA | NA
27/05/2026 | Leave | NA | NA | NA
29/05/2026 | Leave | NA | NA | NA
2026-01-06 | Leave | NA | NA | NA
2026-02-06 | * Setup VDI and raised all the required accesses * Analysed Updated TCs in AT/LOFT Regression suite | List down the improvement areas in the updated TCs in AT/LOFT Regression suite | Multiple browser instances are being opened and need to correct it from parallel execution point of view | NA
2026-03-06 | * Updated TC_3419 automation code TC in AnnTaylor, Loft regression suite, for sprint 26.16 | Reviewing TC_3612 case in AnnTaylor, Loft regression suite for designing automation code, for sprint 26.16 | NA | Since running the code in local, it is time consuming vs lamda test
2026-04-06 | * Completed updating the TC_3419 for AT/Loft Regression suite, for sprint 26.16 | * To start preparing automation script for TC_3612 for AT/Loft Regression suite, for sprint 26.16 | NA | Since running the code in local, it is time consuming vs lamda test

## BDD Framework Issues #
Associates | Issues
Dinesh Ramakrishnan | 1. Mutiple Thread.sleep has been added with more than 20 seconds, which makes the run delayed 2. Assertions should be added more, which is missing in current BDD framework. Ex., Page navigation is not validated with assertions

## KT Video& Document reference
Knitwell KT dcouments | KnitWell_Group - Documents - Documents - All Documents
Knitwell KT Video | Recordings
Internal KT video links- Playwright
Fagun_StandUpcall_MOM | Fagun_Standupcall_Mom - OneDrive

## issues
Name | Issue | Comments
Dinesh Ramakrishnan | Still not yet get the VDI access | Waiting for naveen update on this